DELIVERY KIT  /  IK

# Implementation Kit — Commission, Qualify and Operate

Run the accepted design; record the actual result.

Kit v1.0 • 16 September 2026 • Aligned to the frozen v1.4 reference architecture

Working kit, not an approved site design or deployed platform. Templates, reference examples and live evidence are separate records.

Use this kit after a controlled engineering release. The runbooks identify actions and evidence, while the approved site method supplies exact native commands and configuration. No runbook in this kit is authority to change an environment.

## Section links

1. Implementation workplan and required inputs

2. Work packages, dependencies and authority

3. Staging, bootstrap and physical commissioning

4. Native platform commissioning tracks

5. Shared security, services and protection

6. Restricted qualification and meaningful observations

7. Tenant provisioning and controlled production activation

8. Interrupted work, brownfield adoption and change

9. Operational handover, recovery, migration and retirement

All additional process guidance is proposed kit practice. RA/WD references identify baseline-derived architecture; K references identify external mechanism checks. No site values or approval signatures are supplied.

# 1. Implementation workplan and required inputs

Implementation converts a reviewed design into an observed, supportable service. Installation, qualification, production activation and continuing operation are distinct outcomes.

Baseline and related records: DEL §3  •  EK §8  •  WD §9

| Implementation output | Accountable role | Completion evidence |
| --- | --- | --- |
| IK-01 — Change scope, release freeze and execution authority | Change owner | Actual change reference, immutable artifacts, scope, participants and stop authority recorded. |
| IK-02 — Staging and installation readiness | Deployment lead | Supplier/asset checks, approved installation method, facility work, recovery access and staging results accepted. |
| IK-03 — P0–P1 bootstrap and foundation receipts | Foundation owner | Trusted independent access, minimum services and verified physical/network transport precede platform consumption. |
| IK-04 — P2 native platform build receipts | Selected platform owner | Installer and native resource changes match approved tuple; APIs, baseline and supported recovery observed. |
| IK-05 — P3 shared-service and boundary receipts | Service + edge owners | Denied boundary paths, service clients, return routing, names/trust/backup and management separation observed. |
| IK-06 — Restricted qualification fixture and test campaign | Assurance lead | Authorized disposable scope, actual observations and supporting control paths; no production qualification assumed. |
| IK-07 — G4 initial operational and recovery readiness | Service operations owner | Owners, support, monitoring, incident paths and required restore/recovery evidence accepted before activation. |
| IK-08 — P4–P5 tenant build and production activation | Service acceptance owner | G0/G1/G2, applicable initial G4, current tests and valid authority precede reversible activation. |
| IK-09 — As-built, defect and evidence records | Implementation + operations | Actual identities, configurations, departures, tests, evidence and owner acceptance are attributable. |
| IK-10 — P6 maintenance, migration and retirement | Lifecycle/data owners | Change requalification, fencing, retained-copy/key obligations, access withdrawal and safe disposal tracked. |

Use Implementation_Tracker.xlsx for the execution record. A local workbook status is an index to evidence and authority; it is not an approval engine. Record actual operators and approvers rather than accepting the role names in this reference as assignments.

# 2. Work packages, dependencies and authority

Maintain separate execution scopes even when one delivery workflow coordinates the whole environment. Handoffs pass only the identities, capacity and configuration facts the next owner needs.

Baseline and related records: RA §20  •  PROV §1  •  WD §10

| Package | Execute and observe | Accepted handoff |
| --- | --- | --- |
| P0 — bootstrap | Establish restricted administration, minimum time/name/trust and recoverable tooling. | Accountable temporary dependencies; usable recovery access and custody. |
| P1 — foundation | Commission the accepted hardware, OOB, fabric and attachment capacity. | As-built physical links, routing, MTU, fault behaviour and available slots. |
| P2 — platform | Install the chosen supported stack; configure eligible compute, storage and transport. | Exact tuple, native ownership, baseline and service limitations. |
| P3 — services | Establish security contexts, names, identity, keys, logging and protection. | Published consumption interfaces, return paths and protection/custody. |
| P4 — tenant/domain | Allocate entitled scope, addresses, domains, networks and mandatory policy. | Native identities, eligibility and boundaries under deny. |
| P5 — resources/activation | Create owned VMs/disks, bind services, verify and activate within authority. | Current test evidence, initial operational readiness and accepted live path. |
| P6 — lifecycle | Maintain, expand, recover, migrate or retire under the owning scopes. | Changed as-built records, requalification and retained-data obligations. |

P2 installation can depend on accepted P0 bootstrap services. Complete P2/P3 offered-service acceptance together before ordinary tenant allocation. Record and retire temporary trust deliberately; do not create a circular recovery dependency.

# 3. Staging, bootstrap and physical commissioning

Use RB-00 and RB-01. Staging is part of implementation readiness, not evidence that equipment has been commissioned.

Baseline and related records: RA §21  •  ET §2  •  PROV §2

| Checkpoint | Required action and observation | Stop condition |
| --- | --- | --- |
| Release and scope | Match change authorization, exact inventory, LLD revision, signed/checksummed artifacts and permitted window. | Unapproved change, inconsistent inventory or unknown resource owner. |
| Site safety and physical work | Have qualified personnel perform installation using approved facility and manufacturer procedures. Record completion, access, rack/power/failure-group and cable results. | Missing facility release, unsafe conditions or installation outside the accepted design. |
| Supply and baseline | Verify received equipment, licenses, support, firmware/driver compatibility and trusted software source. Retain media/part custody where required. | Unknown support combination, altered artifact or unaccounted component. |
| Restricted management | Establish the approved console/OOB and initial privileged trust; restrict target access and register temporary grants. | Default credentials or a tenant path exposes privileged management. |
| Minimum dependencies | Verify trusted time/name/identity or approved emergency alternatives, certificate trust and artifact access. | Required dependency has no accepted endpoint or independent recovery method. |
| Foundation observation | Use the approved configuration mechanism; observe links, control policy, MTU, allowed adjacency and surviving access. | Unexpected route/port, missing policy or failed recovery access. |
| Handover | Store actual configuration, ownership, recovery copy, telemetry and open deviations; obtain G1 scope acceptance. | Required observations absent or unresolved critical deviations. |

Do not store production secrets in this kit. Record a protected custody reference and the authorized role. A temporary bootstrap credential is not a permanent exception to separation of duties.

# 4. Native platform commissioning tracks

Use the selected vendor track, not all three stacks simultaneously by default. The same reference service is repeated on the next stack to establish a separate portability claim.

Baseline and related records: VC §2  •  VC §3  •  VC §4  •  RA §22

| Track | Native installation and preparation | Required observations |
| --- | --- | --- |
| Nutanix / RB-02 | Supported AHV/AOS and Prism installation; chosen Flow networking/security; eligible host/controller/storage scope and isolated external handoffs. | Actual VPC/external routing and policy; same-host enforcement; no shared-connected bypass; storage, key and controller dependencies. |
| VMware/NSX / RB-03 | Supported vCenter/ESXi and storage; NSX management, transport/Edge topology, independent domain and upstream contexts. | Actual distributed and service-router paths; gateway mode compatibility; no unauthorized route propagation; DFW ownership and Edge failure behaviour. |
| OpenStack / RB-04 | Selected distribution services, databases/messaging, Keystone/Nova/Placement, Neutron backend, Glance/Cinder and offered services. | Scheduler constraints; provider-owned mandatory network mutation; additive group behaviour; distributed paths, gateway and storage dependencies. |

## Common platform receipt

Record product, API, provider and installer versions; firmware/drivers and hardware; enabled features and entitlements; control and storage placement; resource identity and authoritative writer; accepted management and data paths; actual tests; limitations; and supported upgrade/recovery approach.

Terraform starts at the supported resource API boundary. A native installer can remain the owner of platform installation, upgrades or controller-managed objects. Do not import or directly edit backend objects owned by another control system merely to make every step appear to be Terraform.

A documented vendor feature is not a qualified tuple. KIT-TN-01 adds an explicit NSX parent-gateway mode compatibility check; apply it to the selected release before choosing a Tier-0 VRF realization.

External mechanism context: K05 — Official Nutanix Terraform provider repository  •  K06 — OpenStack Neutron networking concepts  •  K07 — OpenStack OVN reference architecture  •  K08 — OpenStack Nova host aggregates  •  K09 — Broadcom KB 442835 — Tier-0 VRF and active-active stateful HA

# 5. Shared security, services and protection

Use RB-05. Shared services and ZIP capacity are provider infrastructure, not incidental tenant modules.

Baseline and related records: RA §9  •  RA §12  •  SVC §1  •  WD §7

| Service boundary | Commissioning observation | Receipt / responsible owner |
| --- | --- | --- |
| EC/SE and domain handoffs | Correct context membership, permitted prefixes, connected routes, forward/reply symmetry, no alternative inspection bypass; management separately controlled. | Context/interface identities, policies, capacity and test traces / security-edge owner. |
| Names, addresses and time | One authoritative allocator per delegated scope; forward/reverse lifecycle and reuse; DNS UDP/TCP and fallback; selected time service. | Allocations, names, TTL/lease constraints, protocol checks / network-service owner. |
| Identity and privileges | Actual native roles match approved duties; tenant cannot modify baseline or foreign resources; recovery path is controlled. | Role and target-scope review, grant/revocation evidence / identity and platform owners. |
| Certificates and keys | Correct client/issuer/trust relationship, endpoint validation, use versus administration, retained-copy key continuity; no plaintext fallback. | Key/certificate references and observed recovery behaviour / trust custodians. |
| Logging and monitoring | Events carry usable domain/workload identity; approved collection and time; loss/buffering visible; no broad management access. | Event examples, coverage and alert routing / operations owner. |
| Storage and protection | Owned attachments/copies, supported capture path, separate transfer/admin, retained catalogue and protected keys; actual isolated restore. | Copy lineage, protection assignment and restore result / storage and backup owners. |

Service reachability is not service entitlement. A shared resolver or repository must not forward tenant traffic or grant administrative rights. For the dedicated service-handoff example, service replies must select the originating tenant context; a convenient default route is not proof of symmetric enforcement.

# 6. Restricted qualification and meaningful observations

Use RB-06 under an explicit non-production test authorization. Candidate capacity can host a restricted disposable fixture to obtain qualification evidence; that permission is not production acceptance.

Baseline and related records: WD §11  •  WD §13  •  QUAL §5

| Campaign step | What to record | Evidence quality check |
| --- | --- | --- |
| Select scope | Service class, tuple, topology, sharing, families, changed features and requirement assertions. | Select applicable observations; do not make a second qualified stack a prerequisite to the first. |
| Authorize and prepare | Permitted fault/probe scope, disposable data, time window, restoration and stop authority. | Protect unrelated tenants; no intrusive or destructive test outside this scope. |
| Build fixture | Two tenants/four domains; approved services and one temporary sequential same-domain probe. | Peak guest fixture demand is accounted for separately from infrastructure overhead. |
| Prove control paths | Establish healthy endpoints and expected permitted functions before negative observations. | A timeout from a dead endpoint cannot establish a successful isolation result. |
| Observe outcomes | Capture intended versus realized path, native roles, policy, resource/copy ownership, fault and recovery result. | Distinguish security continuity, availability and actual recovery; no success inferred from tool exit alone. |
| Review and release | Record passed, failed, blocked, not-run or justified not-applicable; reviewer and immutable artifact references. | Unexecuted or missing mandatory evidence blocks the corresponding qualification. |

The kit carries 80 historical CT procedures, 12 realization addenda and 12 W14 assertions as reference material. They are not 104 executed tests. Applicability must be resolved for the target, and individual assertions may require several observations.

Use IT §4 for each test execution and IT §5 for recovery. Include the actual tuple, observation time, topology revision and target identity; never prefill an observed result from an expected result.

# 7. Tenant provisioning and controlled production activation

Normal tenant allocation consumes accepted capacity. Production activation has additional prerequisites that a successful infrastructure build cannot waive.

Baseline and related records: RA §23  •  WD §9  •  IT §7

| Sequence | Execute within accepted scope | Stop / preserve |
| --- | --- | --- |
| 1 — Confirm prerequisites | Check G0/G1/G2 for the offered service; confirm current service authority, initial G4 readiness and owner acceptance requirements. | Missing scope or evidence prevents production activation. |
| 2 — Reserve and establish scope | Resolve eligible cell/pools; reserve compute, storage, addresses and edge slots; establish tenant/domain ownership. | No guessed addresses or capacity borrowed from failure reserve. |
| 3 — Denied networks and boundary | Create native networks/gateways and mandatory policies before endpoint connection; configure paired edge routes and flows under their owner. | No fallback public/default route; unverified resources remain isolated. |
| 4 — Resources and services | Use approved images, owned disks and eligible hosts; register names, identities, telemetry and protection. | Do not relax placement or grant broad service-management access to finish a build. |
| 5 — Verify and review | Compare actual placement, attachments, permitted/denied paths, service scope, protection and current evidence. | Unknown, stale or failed mandatory observation keeps the environment restricted. |
| 6 — Controlled activation | Authorized service owner accepts the exact scope; enable only approved exposure and verify the live path. | On failed activation, withdraw exposure while preserving owned data and evidence. |
| 7 — Confirm as-built | Record native identities, actual state, acceptance and support handover. | This confirms already assigned owners; it is not where readiness is first discovered. |

G4 initial readiness precedes G3 production activation. Continuing G4 exercises after activation do not replace the initial proof supporting a promised service. Restricted fixture permission is a separate record.

# 8. Interrupted work, brownfield adoption and change

Use RB-07. A timeout, lost executor lease or revoked credential does not prove that an accepted native operation stopped.

Baseline and related records: PROV §5  •  PROV §6  •  WD §10

| Situation | Safe response | Before work resumes |
| --- | --- | --- |
| Unknown native outcome | Freeze competing writes, identify the owning executor, inspect native tasks and actual side effects. Preserve data and logs. | Accountable owner selects resume, supported compensation or forward repair; resource identity is reconciled. |
| Failed downstream package | Keep incomplete endpoints denied. Release only proven unused reservations; do not delete shared objects or new production data. | Dependent owner accepts the handoff and verifies the changed paths. |
| Stale plan or changed approval | Reject reuse of a plan whose relevant inputs, policies or state no longer match the approved change. | Re-evaluate differences and obtain the correct scope decision. |
| Brownfield adoption | Discover actual ownership and dependency before import; review non-destructive changes and remove dual writers deliberately. | A state import is not compliance or permission to replace live disks/gateways. |
| Emergency containment | Preserve the authorized containment action while reconciling ordinary desired configuration. | Only the designated authority releases the block; record before/after evidence. |
| Upgrade or capacity expansion | Recheck support tuple, survivor capacity, actual rollback limits and changed assurance paths. | Qualify/canary the changed scope before broad promotion; preserve a recovery path. |

A saved Terraform plan can be reviewed offline using the supplied review_tfplan.py. It reports selected review triggers without inspecting secret-bearing before/after values. It does not evaluate all policy semantics, qualify the provider or approve an apply.

External mechanism context: K03 — Terraform providers within modules  •  K04 — Terraform dependency lock file  •  K11 — Terraform plan command reference

# 9. Operational handover, recovery, migration and retirement

Use RB-08 and RB-09. Treat change, recovery and retirement as infrastructure lifecycle operations with data and security consequences.

Baseline and related records: RA §27  •  SVC §6  •  QUAL §7  •  IT §8

| Lifecycle outcome | Required work | Acceptance record |
| --- | --- | --- |
| Operational handover | Confirm support/escalation, actual as-built, telemetry, incident authority, credential custody, capacity limits and maintenance. | Operations accepts a specific service envelope with current evidence, not receipt of generic documentation. |
| Restore or site recovery | Establish authority and fence ambiguous writers; recover trust/catalogue/keys and foundations; restore isolated data and dependencies. | Measured consistency point and recovery time; useful data and required security verified before reconnection. |
| Cross-platform migration | Qualify target, transfer state through bounded approved access, verify device/driver/boot/key/data compatibility and final consistency. | Controlled cutover and feasibility of return after new writes; Terraform is not the data conversion engine. |
| Retirement | Reconcile consumers and holds, create required recovery/export first, withdraw live routes/grants and remove only owned eligible resources. | Remaining copies, keys, owners and disposition are explicit; sanitization receipt before reuse. |
| Continuing acceptance | Revisit actual service targets, exception expiry, support, resource headroom and periodic recovery after material change. | Current scope accepted or restricted; historical authorization is not rewritten. |

Kit completion means the working records and methods are available. Site completion requires filled values, actual execution evidence, independent review where required and decisions by the designated authorities.