DESIGN DEVELOPMENT  /  OPS

# Operations, Recovery and Transition Playbook

Operate the actual service envelope, recover dependencies, and retire without losing data or authority.

Kit release v1.1 • 17 September 2026 • Parent architecture v1.4 retained

Proposed engineering development. Reference examples, site decisions, actual observations and approval remain separate.

This supplement develops IK-07 and IK-10 and the existing recovery/retirement runbooks. It supplies dependency decisions, change handling, a worked recovery timeline and operational records. It does not replace an approved incident process, native product procedure or data-owner decision.

## Section navigation

1. Operate service outcomes rather than isolated components

2. Specify dependency loss before it becomes an incident

3. Run maintenance and recover interrupted changes

4. Recover the service in dependency order

5. Calculate the recovery critical path and data point

6. Migrate and fail back without conflicting writers

7. Retire live service separately from retained data

8. Accept operational responsibility for the delivered scope

Basis: linked RA/WD and role-kit sections retain their original authority. The elaborations, record formats and calculations in this supplement are local proposals, not new government requirements. D-source references identify freshly checked public mechanisms, not installed compatibility. Exact source locators are in 04_Shared/development/source_reviews.csv.

# 1. Operate service outcomes rather than isolated components

The operator needs to know what the service promises, which controls make that promise valid and which team can repair each dependency.

Design basis and related records: RA §26  •  QUAL §7  •  IK §9

| Operating question | Required current record | Decision when the record is missing |
| --- | --- | --- |
| Can new demand be accepted? | Service-class quota, actual commitments and all surviving capacity bottlenecks. | Queue, restrict or choose another already eligible placement; no borrowing security reserve. |
| Is the service still supported? | Installed versions, support horizon, vulnerabilities, exceptions and available recovery method. | Escalate and limit affected capability under the approved lifecycle policy. |
| Why does connectivity exist? | Domain authorities, approved operation, actual route and effective policy. | Investigate or restrict through the responsible authority; reachability is not permission. |
| Can this service be recovered? | Current copy/catalogue/key dependencies, useful restore evidence and accountable recovery owner. | Withdraw an unsupported promise or remediate; a completed backup job is insufficient. |
| Who accepts a change? | Scope owner, affected consumers, operating conditions and evidence dependencies. | Resolve authority before execution; a technical role name is not an assigned approver. |

Define an observation cadence and material-change triggers for each service parameter. This playbook does not invent organization-wide maintenance or incident deadlines. Use the actual service agreement to set response objectives, review intervals, support coverage and escalation contacts.

Monitoring spans data-path success, denied-path enforcement, controller health, storage/copy integrity, identity/key use, native task completion and capacity. Tenant-provided logs alone do not establish provider enforcement. Account for collection loss, clock quality and protected access to cross-tenant evidence.

Continue with: OPS §2  •  OPS §8

# 2. Specify dependency loss before it becomes an incident

Loss behaviour is different for established traffic, new operations and recovery. Record all three using the actual supported implementation.

Design basis and related records: RA §14  •  SVC §6  •  IK §8

| Dependency loss | Existing / new operation | Recovery and authority condition |
| --- | --- | --- |
| Platform manager or runner | Existing data plane follows the qualified behaviour; new uncertain changes pause. | Discover accepted native tasks before restart. Do not infer that a timed-out action stopped. |
| IPAM / naming | Existing addresses and records follow their accepted lease/continuity policy; no guessed new allocation. | Restore authoritative history and reconcile reservations, DNS and actual resources before reuse. |
| Identity / privileged access | No automatic unrestricted local-account fallback for new administrative work. | Use the approved scoped emergency path; retain logs and revoke recovery grants after use. |
| KMS / certificate trust | Running access, cached keys and restart behaviour follow measured scope; no plaintext fallback. | Recover authorized keys/trust independently of resources that require them; preserve retained-copy access. |
| Logging / evidence collection | Enforcement remains; buffering and loss alerts follow the selected profile. | Record missing intervals and apply approved operating restrictions, rather than fabricate complete logs. |
| Storage, edge or site partition | Fail-safe enforcement and writer control precede any promotion or alternate path. | Select the authorized survivor/restore scope; verify capacity, consistency and current policy. |

For each dependency record a named recovery owner, invocation conditions, observable safe state, local evidence location, dependent services and the point at which fresh acceptance is needed. A common identity or key service can couple otherwise separate sites; different site labels do not remove that dependency.

“Fail closed” does not mean destroy workloads or data. It means unavailable authority must not create new permission or bypass. Existing-service continuity follows the approved control and risk conditions.

Continue with: QCP §5  •  OPS §4

# 3. Run maintenance and recover interrupted changes

Classify a change by its effects on service, boundaries and data—not by the repository or tool that performs it.

Design basis and related records: RA §25  •  PROV §5  •  IK §8

| Stage | Owner action | Stop or re-evaluate when |
| --- | --- | --- |
| Bound the change | Identify affected native objects, consumers, supported tuple, surviving load and approved window. | Authority is missing, a shared dependency is undisclosed, or recovery is unproven. |
| Freeze artifacts and ownership | Bind the accepted configuration/plan, actual state and credentials to one execution owner. | Another writer changes the target or approval-sensitive input after review. |
| Observe execution | Use supported native completion signals and capture actual side effects. | The response is lost, timeout expires or the executor lease ends without confirmed native completion. |
| Resolve uncertainty | Freeze competing writes; inspect native tasks, resources and data state; choose resume, forward repair or supported compensation. | A delayed task can still complete or compensation might delete shared or newly written data. |
| Reaccept and hand over | Recheck affected controls, capacity and data; record as-built and remaining defects. | Required observations are stale or incident containment has not been explicitly released. |

A prior state snapshot does not revert the actual infrastructure. Similarly, credential revocation may prevent a new API call without cancelling work already accepted by a native system. Record the remaining task and resource identity, then obtain the owning team’s recovery decision before a new execution competes with it.

For brownfield adoption, discover current routes, policies, data attachments, ownership and dependencies first. Review the non-destructive import/adoption scope and remove conflicting writers deliberately. Adoption is not conformance, and it is not permission to replace existing VMs, disks or gateways.

An authorized incident block takes precedence over ordinary configuration reconciliation until the incident authority releases it. Repair must not restore an old allow path merely because it remains in source.

Continue with: PBS §9  •  QCP §5

# 4. Recover the service in dependency order

Recovery begins with authority and trusted access, not with powering on every available copy of a VM.

Design basis and related records: SVC §6  •  RA §27  •  IT §5

| Recovery stage | Required action | Exit observation |
| --- | --- | --- |
| 1. Establish authority | Declare scope and recovery owner; preserve evidence and prevent ambiguous concurrent writers. | The selected data/service recovery point and writer authority are explicit. |
| 2. Recover minimum trust | Establish approved management/OOB, name/time/identity and access to protected keys and recovery material. | Recovery does not depend solely on the failed encrypted or management platform. |
| 3. Rebuild foundations | Recover accepted configuration, inventory/state, transport, storage and platform control; then denied security and service paths. | Actual resources, support tuple, routes, quorum and shared dependencies match the recovery design. |
| 4. Restore isolated service | Recover owned data, images and required identities/services into eligible domains. | Useful consistency markers, valid credentials/keys and permitted/denied paths are verified. |
| 5. Activate and observe | Obtain required acceptance, switch approved service access and observe the live path. | Writer control, service outcome and achieved recovery targets are recorded. |
| 6. Stabilize and plan return | Re-establish protection, reconcile emergency grants, and plan failback separately. | No temporary path or stale privilege remains without an accountable approved lifetime. |

An isolated restore may reveal compromised configuration, missing keys, stale identities or an unusable consistency point. Keep the result restricted until the responsible owners resolve those conditions. A successful file read is not application acceptance; the service/data owner supplies meaningful restored-state checks.

Avoid recovery loops: the only key to unlock storage cannot be stored only on that locked storage; the sole backup catalogue cannot be reachable only through a destroyed controller. Record a tested dependency cut and custodial recovery method, without publishing secrets in the kit.

Continue with: OPS §5  •  QCP §5

# 5. Calculate the recovery critical path and data point

The following schedule is a local planning example. It is not measured performance, an approved target or a prediction for any vendor platform.

Design basis and related records: QUAL §4  •  SVC §6  •  EK §6

| Example activity | Minutes | Dependency / elapsed finish |
| --- | --- | --- |
| Detect and declare | 10 | Start 0 → finish 10 |
| Select recovery authority | 5 | After detection → finish 15 |
| Recover minimum trust / bootstrap | 25 | After decision → finish 40 |
| Network foundation / storage foundation | 20 / 40 | Illustratively parallel after bootstrap → finish 60 / 80 |
| Restore service data | 35 | After both foundations → finish 115 |
| Validate security and useful data | 20 | After restore → finish 135 |
| Controlled access cutover | 5 | After validation → finish 140 |

With those dependencies, elapsed recovery is 10 + 5 + 25 + max(20, 40) + 35 + 20 + 5 = 140 minutes. Against an illustrative 180-minute target, planning margin is 40 minutes. Do not add both parallel branches or assume independence when they share people, storage, credentials or network recovery. If the two foundation tasks must run serially, the same example becomes 160 minutes with 20 minutes of margin.

Include decision, queue, transfer, validation and exposure time when they fall inside the agreed RTO boundary. The actual service defines the start and end events. Rehearsal evidence determines feasibility; the calculation only reveals assumptions and dependencies.

## RPO is a data-state measurement

If service loss occurs at 12:00 and the latest verified recoverable consistency point is 11:45, the recovered-data age is 15 minutes. A job that finished at 11:55 does not prove an 11:55 data point. Record capture/transaction consistency, replication lag, copy integrity and the actual accepted state. These timestamps are illustrative.

A recovery target can be met while an availability objective is breached. Report both; RTO is not an automatic exclusion from service downtime.

Continue with: QCP §5  •  OPS §8

# 6. Migrate and fail back without conflicting writers

Provisioning target infrastructure and transferring existing workload state are separate activities with separate owners.

Design basis and related records: RA §27  •  PROV §6  •  QCP §7

| Transition stage | Controlled work | Decision before proceeding |
| --- | --- | --- |
| Discover and prepare | Map current data, drivers/boot, virtual devices, identity/keys, network dependencies and accepted target. | The target supports the required service and recoverable data format; unresolved extensions are explicit. |
| Transfer under bounded access | Use the approved capture/transfer method, scoped temporary route/policy and integrity checks. | Data consistency method, bandwidth/window, authority and cleanup owner are accepted. |
| Final consistency and writer change | Select final data point; control old writers; validate target state and service dependencies. | One attributable writer authority exists before target production writes. |
| Cut over and observe | Change only approved DNS/exposure/service access; verify the actual client path and protection. | Operating owner accepts current evidence and the point at which simple rollback ceases to be safe. |
| Return or retire | Reconcile new writes before failback; otherwise retire the source under retention policy. | Reverse synchronization/recovery is supported; old data is not restarted as a competing current copy. |

Before target writes, return to the source may be possible if the original state and authority remain valid. After target writes, restarting the old copy can lose or fork data. The runbook identifies that point of no simple rollback and the required reverse transfer or recovery process. “Rollback” must state its data implications.

Temporary cross-domain transfer access is time-bound and reviewed. Persistent vendor live-mobility and storage-replication transports remain provider infrastructure with their own controlled membership; they are not recreated for each migration just to satisfy a temporary-access rule.

A composite service actively using several stacks is a distinct architecture. Account for cross-stack latency, security edges, identity, shared-service loss and ownership before claiming it provides the same resilience as one bounded cell.

Continue with: OPS §7  •  IT §8

# 7. Retire live service separately from retained data

A retired WSD can leave legitimate protected copies. Make those obligations explicit rather than declaring all data destroyed because live resources were removed.

Design basis and related records: RA §27  •  SVC §4  •  IK §9

| Object / obligation | Retirement decision | Evidence of safe completion |
| --- | --- | --- |
| Shared domains and services | Remove only the departing consumer’s authority; retain objects with other approved dependents. | Dependency review and absence of unintended impact on remaining consumers. |
| Routes, policies, names and addresses | Withdraw obsolete live access, reconcile caches/leases/sessions and quarantine reuse. | Actual residual scan and ownership history, not only a destroy command’s exit status. |
| Snapshots, replicas and backups | Reconcile retention, holds, approved copy locations and data owner. | Known copy inventory, current access boundary and explicit disposal/review date. |
| Keys and recovery catalogue | Retain what authorized copies still require; separate use, recovery and destruction authority. | Verified recoverability and custody until approved final disposal. |
| Media and resource reuse | Use the applicable approved sanitization method and qualified handling process. | Method, scope, verification and exceptions before reassignment. A deleted volume record is insufficient. |

A retained-copy record includes former WSD identity, copy identity, category/location, owner, hold/retention, key/catalogue dependencies, authorized recovery access, review date and final disposition authority. It does not retain unnecessary live tenant access merely because a backup still exists.

If an offline copy, supplier-held media or shared key prevents immediate disposal proof, record the unresolved obligation and its owner. Do not label total destruction complete. Conversely, do not delete a shared key to satisfy one workload’s retirement while other retained data still depends on it.

Physical media handling and equipment disposal use the organization’s approved process and qualified personnel. This playbook records scope, authority and evidence; it does not replace handling or safety procedures.

Continue with: IT §8  •  OPS §8

# 8. Accept operational responsibility for the delivered scope

Operations accepts an actual service and its boundaries—not a generic document package or a green installation status.

Design basis and related records: QUAL §7  •  IT §6  •  IT §7  •  DEL §3

| Acceptance area | What the receiving owner confirms | Working response |
| --- | --- | --- |
| Service and as-built | Actual service scope, native identities, topology, data/management boundaries and accepted variation. | [Enter ops as built scope] |
| Support and escalation | Assigned teams, contacts, coverage, supplier access and supported component versions. | [Enter ops support owner] |
| Monitoring and capacity | Observable service/security indicators, alerts, loss handling, reserves and growth triggers. | [Enter ops monitoring capacity] |
| Recovery and protection | Current copy/key/catalogue custody, useful restore evidence and approved RTO/RPO scope. | [Enter ops recovery evidence] |
| Residual obligations | Defects, exceptions, excluded capabilities, retained data and due/review triggers. | [Enter ops residual obligations] |
| Decision and conditions | Actual receiving authority, initial G4 acceptance, production dependencies and ongoing review. | [Enter ops acceptance decision] |

Initial G4 operational and recovery readiness precedes G3 production activation. The later as-built confirmation records what was activated and handed over; it must not be the first occasion on which support or recovery ownership is discovered. Continuing exercises confirm that the service remains inside its accepted envelope.

A material change can invalidate only part of a qualification or a wider inherited dependency. Record the affected scope, conditions for existing operation, restrictions on new placement and the evidence required for reacceptance. Keep historical authorization and actual current technical status separately attributable.

Current release status: developed operational procedures and editable records supplied. No site acceptance, real recovery measurement, supplier approval or operating authorization is asserted.