## Deliverables
Implementation delivery register
WORKING RECORD • Status records progress; actual evidence and authority must be linked separately.
ID | Deliverable | Owner role | Actual owner | Gate | Status | Completion criteria | Actual evidence | Decision reference
IK-01 | Change scope, release freeze and execution authority | Change owner |  | Before execution | Not started | Actual change reference, immutable artifacts, scope, participants and stop authority recorded.
IK-02 | Staging and installation readiness | Deployment lead |  | G1 | Not started | Supplier/asset checks, approved installation method, facility work, recovery access and staging results accepted.
IK-03 | P0–P1 bootstrap and foundation receipts | Foundation owner |  | G1 | Not started | Trusted independent access, minimum services and verified physical/network transport precede platform consumption.
IK-04 | P2 native platform build receipts | Selected platform owner |  | G2 | Not started | Installer and native resource changes match approved tuple; APIs, baseline and supported recovery observed.
IK-05 | P3 shared-service and boundary receipts | Service + edge owners |  | G2 | Not started | Denied boundary paths, service clients, return routing, names/trust/backup and management separation observed.
IK-06 | Restricted qualification fixture and test campaign | Assurance lead |  | G2 | Not started | Authorized disposable scope, actual observations and supporting control paths; no production qualification assumed.
IK-07 | G4 initial operational and recovery readiness | Service operations owner |  | Before G3 | Not started | Owners, support, monitoring, incident paths and required restore/recovery evidence accepted before activation.
IK-08 | P4–P5 tenant build and production activation | Service acceptance owner |  | G3 | Not started | G0/G1/G2, applicable initial G4, current tests and valid authority precede reversible activation.
IK-09 | As-built, defect and evidence records | Implementation + operations |  | G3/G4 | Not started | Actual identities, configurations, departures, tests, evidence and owner acceptance are attributable.
IK-10 | P6 maintenance, migration and retirement | Lifecycle/data owners |  | G4 continuing | Not started | Change requalification, fencing, retained-copy/key obligations, access withdrawal and safe disposal tracked.

## Work_Packages
P0–P6 execution and accepted handoffs
Installation dependencies are not permission to offer production. Keep separate owners, actual artifacts and handoffs.
ID | Work package | Owner role | Prerequisites | Required handoff | Actual owner | Status | Receipt / limitations
P0 | Bootstrap / trust | Bootstrap owner | G0 for affected scope | Restricted access, minimum trusted services and independent recovery. |  | Not started
P1 | Physical foundation | Foundation owner | P0; accepted site design | OOB, fabric, physical routing/attachments, observed management and failure scope. |  | Not started
P2 | Native platform | Selected platform owner | G1; approved bootstrap dependencies | Installed tuple, eligible pools, storage/overlay and actual native ownership. |  | Not started
P3 | Security / common services | Service and edge owners | Accepted transport; coordinated P2 installation | Boundaries, named services, identity/keys/logging/protection; joint P2/P3 G2 acceptance. |  | Not started
P4 | Tenant / domain | Platform and security owners | G2 for ordinary production; separate restricted-fixture path | Owned scope, addresses, networks, routes and mandatory policy under deny. |  | Not started
P5 | Workload / activation | Service acceptance owner | P4; current tests; initial G4 and operating authority before production G3 | Owned VMs/disks/services, verified boundaries and controlled activation. |  | Not started
P6 | Change / retirement | Lifecycle and data owners | Accepted current scope and authorized change | Safe maintenance/recovery/migration/retirement with retained obligations. |  | Not started

## Build_Steps
Reference methods — actual execution record
61 site-parameterized steps from 10 runbooks. Fill actual target, approved artifact, operator and evidence. There are no executable vendor commands or supplied permissions.
Step ID | Runbook | Reference step | Owner role | Action / expected observation | Stop / preserve | Actual target / artifact | Actual operator | Status | Native task / UTC | Evidence / disposition
RB-00-01 | RB-00 | Identify the delivery | Change owner | Confirm the service, site, tenant/data scope, environment and work package. Expected: Scope and exclusions match the change request. | Stop if the actual target or owner differs. |  |  | Not run
RB-00-02 | RB-00 | Freeze the engineering input | Change owner | Resolve the HLD/LLD revision, drawings, schedules, exact tuple, approved configuration artifacts and hashes. Expected: One controlled build baseline is identified. | Do not substitute moving latest versions or missing configuration. |  |  | Not run
RB-00-03 | RB-00 | Confirm authority and safety | Change owner | Name executors, reviewer, stop/escalation authority, change window and allowed physical or intrusive-test scope. Expected: Required permissions and site safety releases apply to this action. | No authorization or unsafe conditions: do not start. |  |  | Not run
RB-00-04 | RB-00 | Prove access and recovery | Change owner | Verify approved management path, protected credential custody, independent recovery access and data-safe recovery method. Expected: Recovery is usable for the failure this change can cause. | Do not change the only working access path without the accepted recovery arrangement. |  |  | Not run
RB-00-05 | RB-00 | Review competing work | Change owner | Check current owners, native tasks, locks, incidents and relevant resource/policy revisions. Expected: Single authoritative writer; no unresolved late task or stale approval. | Pause and reconcile conflicts rather than overriding them. |  |  | Not run
RB-00-06 | RB-00 | Issue ready-to-execute record | Change owner | Reviewer accepts the bounded MOP; record conditions and expiry. Expected: Execution may proceed only inside the issued scope. | A kit checklist completion is not the authority decision. |  |  | Not run
RB-01-01 | RB-01 | Verify staged inventory | Foundation deployment lead | Reconcile received hardware/software/entitlements against the accepted BOM and trusted source. Expected: Components and firmware/driver tuple are accounted for. | Quarantine mismatched or unverified items; retain custody evidence. |  |  | Not run
RB-01-02 | RB-01 | Accept physical installation | Foundation deployment lead | Qualified personnel complete approved manufacturer/facility installation and record links, racks, power and failure groups. Expected: Physical topology matches the released design. | Do not improvise electrical, lifting or restricted facility procedures. |  |  | Not run
RB-01-03 | RB-01 | Establish bootstrap trust | Foundation deployment lead | Use the supported restricted console/OOB process and controlled temporary identity; provide accepted minimum time/name/trust. Expected: Privileged access is restricted and recoverable without tenant routing. | Do not enable broad workload management reachability to finish bootstrap. |  |  | Not run
RB-01-04 | RB-01 | Commission transport | Foundation deployment lead | Apply the accepted native configuration through the authoritative tool; verify neighbors, allowed routes, MTU and attachment membership. Expected: Observed underlay/fabric matches the selected design. | Unexpected route import or bypass: stop, isolate affected scope and follow supported recovery. |  |  | Not run
RB-01-05 | RB-01 | Verify the failure boundary | Foundation deployment lead | Run only approved link/management fault observations with restoration procedures. Expected: Required access and enforcement survive as specified; interruption measured. | No unapproved fault injection; do not treat denied traffic as proof of availability. |  |  | Not run
RB-01-06 | RB-01 | Release G1 scope | Foundation deployment lead | Handover actual configuration, inventory, recovery copy, telemetry, capacity and limitations. Expected: Dependent platform work consumes accepted foundation capacity. | Open mandatory foundation issue blocks affected consumption. |  |  | Not run
RB-02-01 | RB-02 | Confirm native support | Nutanix platform owner | Resolve cluster, manager, Flow, provider/API and hardware compatibility and enabled feature scope. Expected: Every needed operation has support evidence or an accepted alternative. | A v2 resource name or provider availability is not full support. |  |  | Not run
RB-02-02 | RB-02 | Install under native ownership | Nutanix platform owner | Execute the approved vendor installation/lifecycle artifact with the protected management path. Expected: Native cluster and control services are healthy at the recorded versions. | Use supported recovery on failure; never create a competing configuration owner. |  |  | Not run
RB-02-03 | RB-02 | Establish eligible pools | Nutanix platform owner | Configure approved host/zone/co-residency eligibility, storage/controller membership, templates and protection integration. Expected: Placement and restart constraints cover actual shared dependencies. | Do not treat separate guest networks as physical isolation. |  |  | Not run
RB-02-04 | RB-02 | Commission virtual network capability | Nutanix platform owner | Prepare platform transport and isolated external handoff capacity; verify supported gateway/no-NAT/NAT choice and policy ownership. Expected: Independent domain routing and baseline controls precede endpoints. | Shared connected external paths remain ineligible until isolation is proven. |  |  | Not run
RB-02-05 | RB-02 | Create authorized disposable fixture | Nutanix platform owner | Under restricted test permission, realize the WD logical roles with site allocations and current mandatory policy. Expected: Fixture ownership is stable; partial resources remain denied. | Do not use documentation addresses as actual allocations or introduce production data. |  |  | Not run
RB-02-06 | RB-02 | Qualify and hand over | Nutanix platform owner | Observe relevant W14/CT outcomes, failure and restore; record actual resource create/update/adopt/delete handling. Expected: Accepted capability scope and limitations available for G2. | Unrun or failed mandatory observation remains open. |  |  | Not run
RB-03-01 | RB-03 | Confirm routing-mode compatibility | VMware/NSX platform owners | Validate exact Tier-1/upstream context, parent Tier-0/VRF and HA mode against installed-release documentation and KIT-TN-01. Expected: Selected modes and service functions are supported together. | Do not change a live parent mode merely to satisfy this checklist; require a separate impact-reviewed change. |  |  | Not run
RB-03-02 | RB-03 | Commission compute/storage management | VMware/NSX platform owners | Execute approved native vCenter/ESXi and storage installation, eligible pools, image/boot and management configuration. Expected: Actual placements and data dependencies match the LLD. | Unsupported tuple or hidden shared management boundary blocks service acceptance. |  |  | Not run
RB-03-03 | RB-03 | Commission NSX transport and edge | VMware/NSX platform owners | Establish approved managers, transport nodes/zones, Edge capacity, uplinks and isolated upstream contexts. Expected: Actual distributed and centralized routing roles are identifiable. | No common unrestricted native route table substitutes for the security boundary. |  |  | Not run
RB-03-04 | RB-03 | Protect mandatory endpoint and edge policy | VMware/NSX platform owners | Apply provider-owned groups, policy hierarchy and separately authorized ZIP relationships before workload connection. Expected: Same-host and cross-host controls cannot be widened by tenant mutation. | Unexpected permissive default or override path keeps resources isolated. |  |  | Not run
RB-03-05 | RB-03 | Run restricted fixture and faults | VMware/NSX platform owners | Build the accepted disposable domains/VMs/disks; observe native route propagation, return context, HA/restart and protection. Expected: Observed outcomes support the offered service and actual failure scope. | No unsupported HA or live-migration promise; stop unsafe fault execution. |  |  | Not run
RB-03-06 | RB-03 | Release scoped capability | VMware/NSX platform owners | Record vSphere/NSX ownership, provider lifecycle coverage, actual limits, limitations and evidence. Expected: G2 considers a concrete service/tuple rather than product names. | Missing exact evidence prevents qualification. |  |  | Not run
RB-04-01 | RB-04 | Resolve selected services and backend | OpenStack distribution/service owners | Record Keystone, Nova/Placement, Neutron backend, Glance/Cinder and all offered data/trust/protection services. Expected: No unsupported feature is inferred from generic OpenStack naming. | Distribution or backend uncertainty blocks affected design. |  |  | Not run
RB-04-02 | RB-04 | Install using supported lifecycle tooling | OpenStack distribution/service owners | Deploy the approved controllers/databases/messaging, compute and backend infrastructure under native ownership. Expected: Control/data dependencies and quorum are observed. | Do not manage Neutron-owned OVN objects through a competing raw writer. |  |  | Not run
RB-04-03 | RB-04 | Enforce placement and data boundaries | OpenStack distribution/service owners | Configure actual scheduler/aggregate/trait eligibility, volume backend classes and image/key controls. Expected: Tenant, zone and restart/restore constraints are effective. | Labels without enforced placement do not satisfy isolation. |  |  | Not run
RB-04-04 | RB-04 | Protect network mutation authority | OpenStack distribution/service owners | Implement provider ownership of base mandatory groups, port security, address pairs, routers and external attachments through the supported role model. Expected: Tenant permissions cannot attach an additive allow or disable required protection. | Unbounded tenant editing is not base-service qualification. |  |  | Not run
RB-04-05 | RB-04 | Verify domain and service paths | OpenStack distribution/service owners | Build restricted distinct domains and handoffs; observe distributed routes, gateways, default egress normalization, metadata/boot services and replies. Expected: Approved services work; connected/provider/floating-address shortcuts do not bypass controls. | Avoid blanket deny that hides broken initialization or IPv6 operation. |  |  | Not run
RB-04-06 | RB-04 | Qualify lifecycle and recovery | OpenStack distribution/service owners | Observe supported create/update/adopt/delete, task cleanup, gateway/host failure, Cinder isolation and restore. Expected: Concrete tuple/service accepted or explicitly limited at G2. | Unknown residual ports/routes/grants remain defects. |  |  | Not run
RB-05-01 | RB-05 | Create owned security capacity | Security-edge and shared-service owners | Use the selected supported edge mechanism to instantiate isolated contexts/handoffs and separately protected management. Expected: Only permitted domains and routes belong to each context. | Do not import unrelated tenant routes or expose admin interfaces on the consumption path. |  |  | Not run
RB-05-02 | RB-05 | Establish forward/reply paths | Security-edge and shared-service owners | Configure accepted prefix and source policy, native gateway handoffs and service-side origin-specific replies. Expected: No connected, neighbour, NAT or alternate default path bypasses enforcement. | Wrong or missing reply path remains unavailable rather than being masked by a broad route. |  |  | Not run
RB-05-03 | RB-05 | Publish named service consumption | Security-edge and shared-service owners | Establish actual DNS/time/repository/log/identity endpoints, entitled operations and scoped initiators. Expected: Selected complete protocols work, including applicable DNS TCP/UDP behaviour. | No broad provider subnet or administrative grant for a service binding. |  |  | Not run
RB-05-04 | RB-05 | Establish key and protection custody | Security-edge and shared-service owners | Identify actual key-service client, capture API, data mover, protected copies, catalogue and held-data obligations. Expected: Tenant workloads do not inherit platform capture or key-destruction privileges. | Missing key/catalogue recovery or independent-copy protection blocks the promise. |  |  | Not run
RB-05-05 | RB-05 | Observe continuity and telemetry | Security-edge and shared-service owners | Test approved service/edge outages and restore paths; verify origin attribution, buffering and actual surviving capacity. Expected: Security and service interruption both measured without fallback bypass. | No unsafe fault or reliance on untested caches. |  |  | Not run
RB-05-06 | RB-05 | Accept service handoffs | Security-edge and shared-service owners | Publish actual endpoints, permitted operations, owners, versions, limits and dependencies to downstream packages. Expected: P2/P3 offered capability is accepted before routine consumption. | Incomplete mandatory service blocks dependent activation. |  |  | Not run
RB-06-01 | RB-06 | Choose the authorized path | Tenant deployment and acceptance owners | Record restricted fixture permission or production prerequisites, exact service envelope and tenant owner. Expected: No production permission inferred from test authorization. | Missing actual authorization stops the affected operation. |  |  | Not run
RB-06-02 | RB-06 | Reserve eligible resources | Tenant deployment and acceptance owners | Allocate authoritative addresses, capacity, storage and attachment/security slots; establish tenant/domain scope. Expected: One owned reservation per resource; actual allocation recorded. | No guessed values or use of excluded capacity. |  |  | Not run
RB-06-03 | RB-06 | Build denied topology | Tenant deployment and acceptance owners | Create owned networks, gateways and baseline policy; coordinate paired edge routes/flows under the edge owner. Expected: No endpoint is exposed before mandatory enforcement. | Unverified partial state remains disconnected/quarantined. |  |  | Not run
RB-06-04 | RB-06 | Create protected resources | Tenant deployment and acceptance owners | Instantiate approved images/VMs/disks in eligible pools, then names, service identities, telemetry and protection. Expected: Actual attachments and client/admin boundaries match the LLD. | Do not weaken placement or data custody to complete the request. |  |  | Not run
RB-06-05 | RB-06 | Observe applicable outcomes | Tenant deployment and acceptance owners | Run scoped healthy-control, permitted/denied, resource/role, family and recovery observations. Expected: Actual results and artifacts recorded separately from expected outcomes. | Unknown/failed mandatory results remain open, not passes. |  |  | Not run
RB-06-06 | RB-06 | Complete initial readiness and activate | Tenant deployment and acceptance owners | For production, verify G0/G1/G2/current tests, applicable G4 initial and valid operating authority; execute the approved exposure change and verify it. Expected: Only the accepted service scope becomes active. | Failed live verification withdraws exposure without destroying data. |  |  | Not run
RB-06-07 | RB-06 | Close or retain the fixture | Tenant deployment and acceptance owners | Retire disposable test resources and reconcile reservations or formally accept the authorized continuing scope. Expected: No stale test permissions or orphan resource. | Hold required evidence/data; do not blind-destroy shared resources. |  |  | Not run
RB-07-01 | RB-07 | Stabilize ownership | Current authoritative resource owner | Pause competing changes and establish the actual writer, accepted tasks and incident restrictions. Expected: No second executor makes assumptions about task cancellation. | Do not force-unlock until writer cessation is established by the approved recovery procedure. |  |  | Not run
RB-07-02 | RB-07 | Discover actual effects | Current authoritative resource owner | Compare native resources, addressing, routes, data and state against the last confirmed step. Expected: Unknown outcomes become explicit owned findings. | Do not replay create blindly or infer failure from a lost response. |  |  | Not run
RB-07-03 | RB-07 | Choose safe repair | Current authoritative resource owner | Owner approves resume, supported rollback, forward repair or isolated operator intervention with data effects. Expected: Shared resources and newly written/held data are preserved. | No generic compensation may destroy required data. |  |  | Not run
RB-07-04 | RB-07 | Revalidate change basis | Current authoritative resource owner | Replan affected scope when input, policy, state or authority changed; reconcile supported brownfield ownership/import. Expected: No stale plan or dual controller ownership. | Import alone is neither compliance nor permission for replacement. |  |  | Not run
RB-07-05 | RB-07 | Execute and observe | Current authoritative resource owner | Run approved scoped repair; retain containment until its authority releases it; verify impacted paths/data. Expected: Actual desired and realized state converges with supporting evidence. | Unexpected effects stop further changes and trigger escalation. |  |  | Not run
RB-07-06 | RB-07 | Close and improve | Current authoritative resource owner | Update as-built, source, defects, reservations, custody and runbook lessons. Expected: Unresolved effects remain visible and owned. | Do not rewrite historical approval or hide retained exceptions. |  |  | Not run
RB-08-01 | RB-08 | Declare scope and writer authority | Data and recovery authorities | Identify failed/source/target systems, consistency requirements and permitted recovery action. Fence ambiguous writers by the accepted mechanism. Expected: One authorized write authority and protected evidence. | Do not promote a second writer while ownership is unresolved. |  |  | Not run
RB-08-02 | RB-08 | Restore minimum dependencies | Data and recovery authorities | Recover approved administration, trust, name/time, keys/catalogue and source/configuration access. Expected: Recovery path does not depend solely on the failed platform. | No plaintext, replacement-key or unrestricted privileged fallback. |  |  | Not run
RB-08-03 | RB-08 | Prepare isolated target | Data and recovery authorities | Establish eligible compute/data/network boundaries and required services under deny. Expected: Target supports required image/device/data/identity semantics. | Unsupported conversion or co-residency blocks target use. |  |  | Not run
RB-08-04 | RB-08 | Transfer or restore consistent state | Data and recovery authorities | Use the approved platform/data tool through bounded authorized access; preserve copy lineage and measure actual data point. Expected: Useful consistent data is available and attributable. | A completed job is not evidence of useful recovered data. |  |  | Not run
RB-08-05 | RB-08 | Verify and reconnect | Data and recovery authorities | Check application-owner data acceptance, required security/services and recovery timing before approved DNS/exposure cutover. Expected: Current authority accepts the defined recovered service. | Failed verification keeps target isolated. |  |  | Not run
RB-08-06 | RB-08 | Fail back or retire source | Data and recovery authorities | Plan reverse synchronization after new writes; remove temporary routes/grants and reconcile retained copies. Expected: No stale writer, uncontrolled transition path or destroyed held key. | Starting an old VM is not automatically safe rollback. |  |  | Not run
RB-09-01 | RB-09 | Accept actual operations scope | Service operations and data disposition owners | Confirm owner/on-call/support, monitoring, accepted limits, patch/change process, custody and exercised recovery. Expected: Initial readiness supports the production promise. | Missing actual owner or required restore evidence blocks initial acceptance. |  |  | Not run
RB-09-02 | RB-09 | Plan retirement and preserve obligations | Service operations and data disposition owners | Identify dependent services/shared resources, held copies and keys; complete required export/backup before revoking required paths. Expected: Every remaining obligation has an accountable owner. | Do not delete service access required to preserve held data. |  |  | Not run
RB-09-03 | RB-09 | Withdraw live access | Service operations and data disposition owners | Under the relevant owner, remove exposures, ordinary flows, names, routes and grants; confirm session handling. Expected: No obsolete live connectivity/authority remains. | Do not remove another tenant’s shared domain/service. |  |  | Not run
RB-09-04 | RB-09 | Remove eligible resources | Service operations and data disposition owners | Delete only owned eligible workload/attachments; quarantine address reuse and preserve required history. Expected: Actual native state and inventory agree. | Unknown asynchronous completion or reuse conflict remains blocked. |  |  | Not run
RB-09-05 | RB-09 | Sanitize approved data/media | Service operations and data disposition owners | Use the approved media-appropriate process through qualified personnel; verify key/copy scope and held exceptions. Expected: Reuse is supported by actual sanitization evidence. | Resource-record deletion is not proof of data destruction. |  |  | Not run
RB-09-06 | RB-09 | Close and continue retained custody | Service operations and data disposition owners | Retain tombstone, evidence, obligations, access/key custody and future review/disposal dates. Expected: Live service retired; residual data remains explicitly controlled. | Do not mark total destruction while copies remain. |  |  | Not run

## Test_Applicability
Reference procedures and assertions — applicability
80 CT procedures + 12 realization addenda + 12 W14 assertions. These 104 rows are not 104 executed tests; a compound assertion can need multiple observations.
Reference ID | Record type | Title / assertion | Expected outcome | Inherited mappings | Source | Applicability | Actual service / tuple / family | Campaign stage | Rationale / approving authority
CT-001 | CT procedure | Cross-tenant IPv4 isolation | All unapproved flows are denied; positive controls succeed; no misleading pass caused by a dead endpoint. | TEN-001; SDI-002; TEST-001; DEL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-002 | CT procedure | Cross-tenant IPv6 isolation | Unapproved IPv6 flows are denied without breaking required local IPv6 operation. | TEN-001; SDI-002; IPV6-001; IPV6-002; TEST-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-003 | CT procedure | Zone-boundary bypass prevention | No undeclared path exists; allowed traffic is enforced by the ZIP realization; removing that authorization denies it. | ARCH-003; ZIP-001; ZIP-007; OVL-002; RTE-002; IPV6-002; NUT-002; NSX-002; NSX-003; TEST-001; MIG-002; DEL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-004 | CT procedure | Infrastructure management isolation | Workloads cannot access infrastructure management; dedicated authorized administration still works. | ARCH-004; MODEL-002; ZIP-004; MGT-001; MGT-005; BKP-001; DEL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-005 | CT procedure | Default Internet denial | No unapproved egress succeeds; no default-route or NAT shortcut defeats policy. | EGR-001; OS-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-006 | CT procedure | Public ingress protection | Direct exposure is denied; the approved ingress reaches only its declared backend and port. | ING-001; ING-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-007 | CT procedure | Approved stateful flow | Intended request/reply works; reverse initiation is allowed only when separately declared. | ZIP-003; NSX-002; FLOW-001; TEST-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-008 | CT procedure | Service-binding scope | Only declared service endpoints/directions are reachable; consuming one service does not expose its subnet or management. | INV-004; MODEL-002; SVC-001; SVC-002; SVC-003; DEL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-009 | CT procedure | Route-authority integrity | No unauthorized route or advertisement exists; summaries cannot expose excluded domains. | INV-003; RTE-001; RTE-002; RTE-003; RTE-004; FAB-002; EVPN-001; NSX-002; POL-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-010 | CT procedure | Security-event attribution | Records identify tenant, WSD/domain, policy, actor, timestamp and deployment; timestamps satisfy the logging profile. | EGR-002; OBS-001; OBS-002; OBS-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-011 | CT procedure | Control-plane loss | Existing approved paths retain enforcement; new unsafe changes stop; recovery converges without bypass. | INV-007; AUTO-001; TEST-004; FAIL-001; FAIL-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-012 | CT procedure | Security-edge node failure | No unauthorized traffic is permitted; recovery and remaining capacity meet the accepted profile. | REL-001; REL-002; TEST-004; CAP-001; FAIL-001; FAIL-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-013 | CT procedure | Offboarding residuals | Active connectivity and grants are removed; retained copies are explicitly owned/locked; the tombstone explains every remaining object. | IPAM-003; LIFE-001; LIFE-002; DEL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-014 | CT procedure | Security drift detection | Drift changes technical compliance status and alerts the owner; incident containment is not silently reverted. | IMG-002; DRIFT-001; DRIFT-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-015 | CT procedure | Platform/provider upgrade regression | No mandatory outcome regresses; the new certification is approved before broad placement. | PORT-001; QUAL-001; NUT-001; NUT-004; NSX-003; OS-003; FUT-001; TF-002; TEST-002; VULN-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-016 | CT procedure | Portable contract and object identity | Equivalent mandatory intent is preserved; unsupported capabilities reject placement rather than silently degrade. | ARCH-001; INV-001; INV-005; REF-001; REF-002; WSD-002; OVL-001; PORT-003; API-001; TF-003; DEL-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-017 | CT procedure | Admission and authorization negatives | All invalid or unauthorized requests are rejected before any allocation or provider action. | ARCH-001; CAT-001; CAT-002; MODEL-001; WSD-001; WSD-002; ZONE-001; API-002; API-003; POL-001; EXC-003; ONB-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-018 | CT procedure | Unsupported capability and expired certification | Placement fails with an actionable capability reason; candidate/expired records cannot authorize production. | SCOPE-001; REF-002; CAT-002; SDI-003; OVL-001; IPV6-003; PLACE-001; PORT-001; PORT-002; QUAL-001; NUT-001; OS-003; FUT-001; FUT-002; ASSUR-002; ASSUR-003; TEST-002; ONB-001; ACPT-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-019 | CT procedure | Ownership, quota and separation of duties | Only allowed roles succeed; quota reservation is atomic; no resource is created above a hard entitlement. | TEN-001; TEN-002; TEN-003; MGT-003; IAM-001; SVCM-001; NSX-001; OS-002; API-002; STATE-001; SEC-002; OPS-001; OPS-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-020 | CT procedure | Security-label integrity | Tenant changes cannot expand effective permissions; mandatory policy precedence is preserved. | MICRO-002; MICRO-003; NUT-003; NSX-001; FLOW-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-021 | CT procedure | Same-domain east-west isolation | Unapproved east-west communication is denied; allowed flows and required local services function. | SDI-002; OVL-002; MICRO-001; MICRO-003; OS-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-022 | CT procedure | Spoofing and virtual NIC controls | Source identities cannot impersonate another domain; platform exceptions have explicit owners and expiration. | OVL-003; MICRO-003; OS-002; OS-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-023 | CT procedure | Shared edge-attachment isolation | No path bypasses per-domain identity and ZIP enforcement; otherwise the shared attachment is ineligible. | ZIP-002; ZIP-007; OVL-002; RTE-002; RTE-004; EDGE-001; EDGE-002; NUT-002; NUT-004; OS-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-024 | CT procedure | Stateful symmetry and policy routing | Stateful enforcement remains correct; unsupported asymmetry is denied, not resolved by permissive bypass. | RTE-004; EDGE-001; EDGE-002; EVPN-002; NUT-002; NSX-003; FAIL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-025 | CT procedure | Zone adjacency and joint authority | Invalid graphs are rejected; valid bindings resolve to the explicitly authorized adjacent domains. | ARCH-003; INV-002; MODEL-001; SDI-001; SDI-004; ZONE-001; ZONE-002; ZIP-002; ZIP-003; SVC-002; ING-001; FAB-003; POL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-026 | CT procedure | MZ, OOB and remote administration | MZ semantics and OOB transport remain distinct; only approved privileged paths reach management targets. | ARCH-004; MODEL-002; TEN-002; ZIP-004; ZIP-005; MGT-001; MGT-002; MGT-005; IAM-002; FAB-004 | Historical CT catalogue; actual applicability required | Unresolved
CT-027 | CT procedure | Break-glass and identity-provider loss | Access remains accountable and scoped; no shared anonymous administrator or permanent bypass is created. | MGT-002; MGT-004; IAM-001; IAM-002; SEC-003; FAIL-002; FAIL-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-028 | CT procedure | Workload identity and certificate lifecycle | Approved service continues with new material; old/revoked credentials are unusable within the accepted propagation interval. | SVC-003; IAM-001; IAM-003; CRY-001; CRY-003; SEC-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-029 | CT procedure | IPAM concurrency, overlap and exhaustion | One authoritative reservation per allocation; retries are idempotent; exhaustion/unauthorized overlap stops provisioning. | IPAM-001; IPAM-002; IPAM-004; AUTO-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-030 | CT procedure | DNS/DHCP lifecycle and reuse | No duplicate active ownership or premature reuse; stale records disappear within the approved timing profile. | IPAM-001; IPAM-003; IPAM-004 | Historical CT catalogue; actual applicability required | Unresolved
CT-031 | CT procedure | IPv6 local control and IPv4-only posture | No alternate-protocol bypass; enabled IPv6 works correctly and disabled service does not create ungoverned reachability. | RTE-004; IPV6-001; IPV6-002; IPV6-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-032 | CT procedure | MTU and path-MTU discovery | Accepted MTU is reachable without silent black holes; required PMTU feedback is delivered or a documented alternative works. | IPV6-001; IPV6-003; EDGE-001; FAB-004; EVPN-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-033 | CT procedure | BGP and EVPN import/export boundaries | Only authorized advertisements install; route leaks, excess prefixes and unapproved defaults are rejected and alerted. | INV-003; RTE-001; FAB-004; EVPN-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-034 | CT procedure | Leaf/link and multihoming failures | No loop, unintended duplicate forwarding or security bypass; measured convergence meets the fabric profile. | FAB-004; EVPN-002; TEST-004 | Historical CT catalogue; actual applicability required | Unresolved
CT-035 | CT procedure | Compute co-residency and evacuation | Placement, migration and HA restart all preserve the approved co-residency rules; insufficient eligible capacity rejects the action. | THR-001; SDI-001; SDI-003; SDI-004; ZIP-005; SITE-004; CMP-001; CMP-003; PLACE-001; FUT-003; ASSUR-001; ASSUR-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-036 | CT procedure | Hypervisor and firmware baseline | All mandatory baseline items are enforced; unsupported or unattested hosts are ineligible for the affected profile. | CMP-002; IMG-001; IMG-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-037 | CT procedure | Storage tenant isolation | Only the owning or explicitly authorized scope accesses data; no clone or mount circumvents zone/categorization policy. | SVC-001; STO-001; FUT-003; ASSUR-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-038 | CT procedure | Encryption, key isolation and KMS outage | No unauthorized decrypt or plaintext fallback; documented cache/restart behavior matches policy; recovery preserves authorized data. | SITE-004; CRY-001; CRY-002; CRY-003; BKP-004; FAIL-002; FAIL-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-039 | CT procedure | Storage performance and contention | Class limits and protected minimums hold under the accepted failure budget; overload rejects growth rather than bypassing controls. | CMP-002; STO-002; REL-002; CAP-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-040 | CT procedure | Golden image provenance | Only eligible images deploy; exceptions are explicit; rebuild output links to its source and component inventory. | IMG-001; IMG-002; VULN-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-041 | CT procedure | Patch and vulnerability lifecycle | No asset or firmware layer is omitted; overdue risk escalates; roll-forward/rollback preserves service and security. | IMG-001; SUP-001; VULN-001; VULN-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-042 | CT procedure | Supply-chain and package provenance | Tampered/unapproved artifacts never reach a privileged apply; lockfile changes require reviewed provenance. | TF-001; TF-002; TF-005; CICD-002; SUP-001; VULN-001; VULN-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-043 | CT procedure | Terraform plan and state confidentiality | Secrets are absent where promised; unavoidable secret-bearing artifacts remain encrypted, access-controlled and redacted from logs. | TF-001; STATE-002; SEC-001; SEC-003; SEC-004 | Historical CT catalogue; actual applicability required | Unresolved
CT-044 | CT procedure | State locking, recovery and grants | Only one writer operates; restore is auditable; unauthorized state reads/writes fail; state rollback is not misrepresented as resource rollback. | MGT-003; TF-003; TF-004; STATE-001; STATE-002; STATE-003; SEC-002; SEC-004; FAIL-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-045 | CT procedure | Partial apply and compensation | No duplicate allocation or accidental destruction; unfinished resources remain quarantined; the journal supports safe resume or controlled compensation. | INV-007; IPAM-004; NUT-004; AUTO-001; AUTO-002; AUTO-003; STATE-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-046 | CT procedure | Retries, optimistic concurrency and idempotency | Replay returns the existing operation; stale updates conflict; one desired generation yields one accountable realization. | IPAM-004; API-003; AUTO-002; AUTO-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-047 | CT procedure | API rate limit and backpressure | Backpressure is visible and bounded; retry honors policy/jitter; permanent errors do not loop indefinitely or consume unbounded capacity. | AUTO-003; CAP-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-048 | CT procedure | Approved-plan freshness | Stale/unapproved plans are rejected and replanned; approved artifacts bind source, inputs, policy, identity and expiration. | SDI-004; POL-002; AUTO-002; TF-002; TF-005; CICD-001; CICD-002; EVID-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-049 | CT procedure | Evidence integrity and authorization separation | Tampering is detected; technical status never self-issues authorization; readiness follows current evidence and decision conditions. | INV-006; AUTH-001; DRIFT-001; TEST-003; EVID-001; EVID-002; EVID-003; OBS-001; IR-002; ONB-001; ACPT-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-050 | CT procedure | Telemetry outage, buffering and retention | Loss/overflow is alerted; buffering behavior matches profile; mandatory evidence gaps are visible; no silent control bypass. | OBS-002; OBS-003; FAIL-002; FAIL-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-051 | CT procedure | Backup administrative separation and immutability | Compromised production authority cannot alter the protected copy or its retention; authorized actions are separately accountable. | BKP-001; BKP-003; BKP-004 | Historical CT catalogue; actual applicability required | Unresolved
CT-052 | CT procedure | Application-consistent isolated restore | Recovered data meets consistency/RPO and recovery timing; no production connection appears until authorized. | SITE-003; STO-002; BKP-002; BKP-003; REL-001; FAIL-001; REC-001; REC-002; DEL-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-053 | CT procedure | Backup retention, holds and key survival | Hold and retention are enforced; key lifetime supports required recovery; data is not prematurely destroyed. | STO-001; STO-003; CRY-002; BKP-003; BKP-004; LIFE-002; LIFE-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-054 | CT procedure | Site loss, fencing and failback | No split-brain or policy relaxation; measured RTO/RPO and data ownership match the recovery profile. | SITE-001; SITE-002; SITE-003; SITE-004; BKP-002; REL-001; REL-002; TEST-004; FAIL-002; FAIL-003; REC-001; REC-002; MIG-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-055 | CT procedure | Management/control-plane bootstrap recovery | Recovery does not require the unavailable production service it is restoring; credentials and old state remain accountable. | MGT-005; SITE-001; CRY-003; STATE-002; FAIL-002; FAIL-003; REC-001; REC-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-056 | CT procedure | Resource and address capacity exhaustion | Requests stop with an explicit reason; required HA/security headroom is not consumed or silently weakened. | CMP-001; REL-002; PLACE-001; SVCM-001; CAP-001; CAP-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-057 | CT procedure | Incident quarantine and reconciler precedence | Containment persists under higher-priority incident policy until released; unrelated tenants remain available. | TEN-003; SUP-001; DRIFT-001; DRIFT-002; DRIFT-003; IR-001; IR-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-058 | CT procedure | Exception approval and expiry | No unapproved exception grants access; expiry changes posture and triggers the documented action without indiscriminate destruction. | RTE-003; CICD-001; DRIFT-003; ASSUR-003; EVID-003; IR-002; MIG-001; EXC-001; EXC-002; EXC-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-059 | CT procedure | Data sanitization and resource reuse | New tenant cannot recover prior data; retained evidence identifies method, scope, exceptions and all surviving copies. | STO-003; CRY-002; FUT-003; LIFE-001; LIFE-002; LIFE-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-060 | CT procedure | Portability and exit rehearsal | Consumer semantics survive; downtime, data loss, format limitations and cost drivers are recorded; no untested live-migration claim. | INV-005; REF-001; STO-002; PLACE-003; PORT-003; REC-002; MIG-001; MIG-002; MIG-003; DEL-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-061 | CT procedure | Location, privacy and support access | Nonconforming placement/access is rejected; exceptions require the designated authority; residency is not asserted to settle jurisdiction. | IPAM-002; SITE-004; PLACE-001; PLACE-002; PORT-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-062 | CT procedure | Shared responsibility and control inheritance | No control is ownerless; inherited evidence is scoped, current and accepted; gaps block required readiness. | SCOPE-001; STD-001; STD-002; CAT-001; THR-001; WSD-003; CMP-003; REL-001; SVCM-001; RESP-001; ASSUR-001; ASSUR-002; OPS-001; OPS-002; EXC-001; ONB-001; ACPT-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-063 | CT procedure | Public certificate and trusted proxy identity | TLS identity is validated; backend trust is explicit; untrusted headers cannot impersonate the originating client. | ING-002; EXP-001; CRY-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-064 | CT procedure | Egress policy and service-specific protocols | Only approved egress semantics work; DNS/FQDN changes cannot silently widen policy; NAT is not treated as a security control by itself. | EGR-001; EGR-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-065 | CT procedure | Privileged workload and container isolation | Unapproved privilege escalation or host access is denied; namespace alone is not accepted as a qualified zone boundary. | MICRO-003; FUT-001; FUT-002; FUT-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-066 | CT procedure | Policy precedence and immutable baseline | Mandatory denies cannot be overridden by tenant policy; membership changes do not create a transient unrestricted interval. | ZONE-002; ZIP-003; OVL-003; MICRO-001; MICRO-002; NUT-003; NSX-001; OS-001; POL-001; POL-002; FLOW-001; DRIFT-003; IR-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-067 | CT procedure | ZIP sensors, heightened posture and authority | Posture change restricts intended flows, preserves declared essentials, and leaves a complete joint-authority record. | ZIP-006; IR-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-068 | CT procedure | Time synchronization and correlation | Excess skew is detected; certificate/evidence validation follows defined failure behavior; record ordering remains explainable. | OBS-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-069 | CT procedure | Technical readiness gate | Service Ready is false unless every mandatory condition for the current generation is satisfied. | INV-006; AUTH-001; CAT-001; WSD-003; OVL-003; EXP-001; RESP-001; QUAL-001; AUTO-002; ASSUR-003; TEST-003; EVID-001; EVID-002; EVID-003; OPS-002; EXC-002; EXC-003; ONB-001; DEL-001; ACPT-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-070 | CT procedure | Contract upgrades and deletion finalizers | No silent security expansion; shared resources survive while referenced; deletion cannot bypass approved finalizers. | INV-001; MODEL-001; TEN-003; WSD-001; API-001; API-003; TF-004; STATE-003; LIFE-001; LIFE-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-071 | CT procedure | Foundation stability for overlay lifecycle | No per-WSD switch change occurs; physical-capacity growth is classified as a separate foundation operation. | ARCH-002; EDGE-001; FAB-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-072 | CT procedure | Bare-metal/fabric-routed service boundary | Consumer contract remains portable; exceptions to overlay workflow are explicit; no unrestricted cross-domain route is introduced. | ARCH-002; FAB-001; FAB-002; FAB-003; EVPN-001; FUT-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-073 | CT procedure | Image/data export compatibility | Incompatibilities reject the selected exit path; data/identity are not assumed portable merely because a disk file converts. | CMP-002; PLACE-003; PORT-003; MIG-003; DEL-002 | Historical CT catalogue; actual applicability required | Unresolved
CT-074 | CT procedure | Procured-capacity and service inventory reconciliation | No orphaned or double-counted capacity; unused procured capacity and support expiry are visible for planning. | SVCM-002; CAP-003; VULN-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-075 | CT procedure | Document and catalogue completeness | No missing or dangling item; counts and release digest agree; document status does not claim unexecuted platform tests passed. | DOC-001; STD-001; STD-002; TEST-003; EVID-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-076 | CT procedure | External partner agreement and revocation | Revocation removes intended access within the agreed interval; no REZ assumption is inferred merely from a private circuit. | ZONE-001; MIG-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-077 | CT procedure | Flow revocation and live session semantics | New sessions are denied immediately upon committed policy; existing sessions are terminated or drained within the explicitly approved interval. | ZIP-006; RTE-003; SVC-003; EXP-001; IAM-003; FLOW-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-078 | CT procedure | Storage clone, snapshot and export classification | Data copies preserve classification and key/access constraints; unapproved downgrade or public export is denied. | STO-001; STO-003; LIFE-002; MIG-003 | Historical CT catalogue; actual applicability required | Unresolved
CT-079 | CT procedure | Provider/support access time limit | No unattended permanent privileged access remains; transferred diagnostics follow approved location and redaction rules. | MGT-004; IAM-002; IAM-003; PLACE-002; SEC-002; OPS-001 | Historical CT catalogue; actual applicability required | Unresolved
CT-080 | CT procedure | Distributed ZIP equivalence | Logical ZIP semantics are fully met; missing inspection, attribution, failure isolation or authority support rejects qualification. | INV-002; THR-001; ZIP-001; ZIP-005; ZIP-006; ZIP-007; OVL-001; EDGE-002; PORT-001; NUT-004; NSX-003; OS-003; FUT-001 | Historical CT catalogue; actual applicability required | Unresolved
RA-01 | Realization addendum | Independent native domain routing | Only the approved logical ZIP path is usable; native forwarding cannot bypass it. | CT-003; CT-009; CT-023; CT-025 | Historical realization addenda; actual applicability required | Unresolved
RA-02 | Realization addendum | NSX isolated upstream reference | Independent domains remain isolated; the approved stateful path and session behaviour match the profile. | CT-003; CT-024; CT-080 | Historical realization addenda; actual applicability required | Unresolved
RA-03 | Realization addendum | Nutanix external attachment reference | Sharing physical transport does not create direct VPC-to-VPC or workload-to-management access. | CT-023; CT-024; CT-031 | Historical realization addenda; actual applicability required | Unresolved
RA-04 | Realization addendum | OpenStack backend and authority reference | Tenant operations cannot remove mandatory isolation, create an unapproved external path or bypass the intended boundary. | CT-017; CT-021; CT-022; CT-066 | Historical realization addenda; actual applicability required | Unresolved
RA-05 | Realization addendum | Physical and platform overlay demarcation | Fabric interoperability does not import tenant routes or federate vendor overlays outside approved scope. | CT-032; CT-033; CT-034 | Historical realization addenda; actual applicability required | Unresolved
RA-06 | Realization addendum | Bootstrap ownership transition | No circular recovery dependency or untracked residual bootstrap privilege remains. | CT-026; CT-027; CT-055 | Historical realization addenda; actual applicability required | Unresolved
RA-07 | Realization addendum | Composite provider authority | Coordination does not create a shared all-powerful state/identity or destroy shared/data resources on failure. | CT-019; CT-043; CT-044; CT-045 | Historical realization addenda; actual applicability required | Unresolved
RA-08 | Realization addendum | Persistent platform versus temporary transfer networks | Persistent platform operation remains within its authority; temporary transfer access is removed without dismantling platform foundations. | CT-035; CT-054; CT-060; CT-076 | Historical realization addenda; actual applicability required | Unresolved
RA-09 | Realization addendum | Brownfield non-destructive adoption | No unapproved replacement or competing writer is introduced; adoption does not falsely assert compliance. | CT-044; CT-048; CT-070 | Historical realization addenda; actual applicability required | Unresolved
RA-10 | Realization addendum | Activation sequencing | No unprotected creation window; failed activation withdraws exposure while preserving data-safe recovery. | CT-006; CT-007; CT-045; CT-069; CT-077 | Historical realization addenda; actual applicability required | Unresolved
RA-11 | Realization addendum | Compute, management and storage sharing | Actual co-residency and shared dependencies match the approved isolation design, including recovery states. | CT-026; CT-035; CT-037; CT-078 | Historical realization addenda; actual applicability required | Unresolved
RA-12 | Realization addendum | Commissioned capacity and growth boundary | The workflow queues/rejects or selects eligible capacity; it does not rewire the fabric or weaken isolation as an undocumented tenant operation. | CT-056; CT-071; CT-072; CT-074 | Historical realization addenda; actual applicability required | Unresolved
W14-01 | Worked-design assertion | W14-01 / routing completeness | Every domain, edge, service next hop and return path matches the approved schedule. | CT-003, CT-009, CT-023, CT-024 / NOT RUN | WD v1.4 §13 | Unresolved
W14-02 | Worked-design assertion | W14-02 / service isolation | Only named service endpoints and authorized resource scope are reachable; router/admin and other tenant targets deny. | CT-004, CT-008, CT-037 / NOT RUN | WD v1.4 §13 | Unresolved
W14-03 | Worked-design assertion | W14-03 / mandatory policy authority | Tenant roles cannot attach a permissive group, disable port security or create an alternative native path. | CT-019, CT-020, CT-022, CT-066 / NOT RUN | WD v1.4 §13 | Unresolved
W14-04 | Worked-design assertion | W14-04 / family completeness | Each offered address family has working allocation, routes, service replies, local controls and recovery. | CT-002, CT-031, CT-032 / NOT RUN | WD v1.4 §13 | Unresolved
W14-05 | Worked-design assertion | W14-05 / DNS completeness | UDP, direct TCP and truncation/fallback work only against approved resolvers. | CT-008 plus explicit protocol observations / NOT RUN | WD v1.4 §13 | Unresolved
W14-06 | Worked-design assertion | W14-06 / intra-domain fixture | Temporary probe verifies same-host and cross-host controls where that placement is approved. | CT-021, CT-035 / NOT RUN | WD v1.4 §13 | Unresolved
W14-07 | Worked-design assertion | W14-07 / admission accounting | Compute, data, context, service and edge commitments fit the same accepted failure basis. | CT-039, CT-056, CT-074 / NOT RUN | WD v1.4 §13 | Unresolved
W14-08 | Worked-design assertion | W14-08 / lost executor | Accepted native tasks and side effects are discovered; no duplicate allocation or competing writer appears. | CT-044, CT-045, CT-046 / NOT RUN | WD v1.4 §13 | Unresolved
W14-09 | Worked-design assertion | W14-09 / activation dependencies | Production activation rejects missing applicable operating or promised recovery readiness. | CT-062, CT-069 plus G3/G4 review / NOT RUN | WD v1.4 §13 | Unresolved
W14-10 | Worked-design assertion | W14-10 / shared-service failure | Permitted and denied paths retain the selected policy and declared service behavior during approved failure. | CT-011, CT-012, CT-024, CT-050 / NOT RUN | WD v1.4 §13 | Unresolved
W14-11 | Worked-design assertion | W14-11 / retained recovery | Required copy, catalogue and key access survive live WSD retirement; unauthorized destruction denies. | CT-051, CT-052, CT-053, CT-078 / NOT RUN | WD v1.4 §13 | Unresolved
W14-12 | Worked-design assertion | W14-12 / second-stack outcome | Repeat the declared environment and representative data recovery on a second eligible stack. | CT-016, CT-060, CT-073 / NOT RUN | WD v1.4 §13 | Unresolved

## Test_Results
Actual test execution and evidence
One starter row per reference. Duplicate a row with a new execution ID for another family, topology or assertion. Expected outcomes remain in Test_Applicability; never copy them into observations as a pass.
Execution ID | Reference ID | Result | Actual tuple / topology | Preconditions / healthy control | Observed result / UTC | Evidence reference / digest | Reviewer / authority | N/A rationale / defect
EXEC-001 | CT-001 | Not run
EXEC-002 | CT-002 | Not run
EXEC-003 | CT-003 | Not run
EXEC-004 | CT-004 | Not run
EXEC-005 | CT-005 | Not run
EXEC-006 | CT-006 | Not run
EXEC-007 | CT-007 | Not run
EXEC-008 | CT-008 | Not run
EXEC-009 | CT-009 | Not run
EXEC-010 | CT-010 | Not run
EXEC-011 | CT-011 | Not run
EXEC-012 | CT-012 | Not run
EXEC-013 | CT-013 | Not run
EXEC-014 | CT-014 | Not run
EXEC-015 | CT-015 | Not run
EXEC-016 | CT-016 | Not run
EXEC-017 | CT-017 | Not run
EXEC-018 | CT-018 | Not run
EXEC-019 | CT-019 | Not run
EXEC-020 | CT-020 | Not run
EXEC-021 | CT-021 | Not run
EXEC-022 | CT-022 | Not run
EXEC-023 | CT-023 | Not run
EXEC-024 | CT-024 | Not run
EXEC-025 | CT-025 | Not run
EXEC-026 | CT-026 | Not run
EXEC-027 | CT-027 | Not run
EXEC-028 | CT-028 | Not run
EXEC-029 | CT-029 | Not run
EXEC-030 | CT-030 | Not run
EXEC-031 | CT-031 | Not run
EXEC-032 | CT-032 | Not run
EXEC-033 | CT-033 | Not run
EXEC-034 | CT-034 | Not run
EXEC-035 | CT-035 | Not run
EXEC-036 | CT-036 | Not run
EXEC-037 | CT-037 | Not run
EXEC-038 | CT-038 | Not run
EXEC-039 | CT-039 | Not run
EXEC-040 | CT-040 | Not run
EXEC-041 | CT-041 | Not run
EXEC-042 | CT-042 | Not run
EXEC-043 | CT-043 | Not run
EXEC-044 | CT-044 | Not run
EXEC-045 | CT-045 | Not run
EXEC-046 | CT-046 | Not run
EXEC-047 | CT-047 | Not run
EXEC-048 | CT-048 | Not run
EXEC-049 | CT-049 | Not run
EXEC-050 | CT-050 | Not run
EXEC-051 | CT-051 | Not run
EXEC-052 | CT-052 | Not run
EXEC-053 | CT-053 | Not run
EXEC-054 | CT-054 | Not run
EXEC-055 | CT-055 | Not run
EXEC-056 | CT-056 | Not run
EXEC-057 | CT-057 | Not run
EXEC-058 | CT-058 | Not run
EXEC-059 | CT-059 | Not run
EXEC-060 | CT-060 | Not run
EXEC-061 | CT-061 | Not run
EXEC-062 | CT-062 | Not run
EXEC-063 | CT-063 | Not run
EXEC-064 | CT-064 | Not run
EXEC-065 | CT-065 | Not run
EXEC-066 | CT-066 | Not run
EXEC-067 | CT-067 | Not run
EXEC-068 | CT-068 | Not run
EXEC-069 | CT-069 | Not run
EXEC-070 | CT-070 | Not run
EXEC-071 | CT-071 | Not run
EXEC-072 | CT-072 | Not run
EXEC-073 | CT-073 | Not run
EXEC-074 | CT-074 | Not run
EXEC-075 | CT-075 | Not run
EXEC-076 | CT-076 | Not run
EXEC-077 | CT-077 | Not run
EXEC-078 | CT-078 | Not run
EXEC-079 | CT-079 | Not run
EXEC-080 | CT-080 | Not run
EXEC-081 | RA-01 | Not run
EXEC-082 | RA-02 | Not run
EXEC-083 | RA-03 | Not run
EXEC-084 | RA-04 | Not run
EXEC-085 | RA-05 | Not run
EXEC-086 | RA-06 | Not run
EXEC-087 | RA-07 | Not run
EXEC-088 | RA-08 | Not run
EXEC-089 | RA-09 | Not run
EXEC-090 | RA-10 | Not run
EXEC-091 | RA-11 | Not run
EXEC-092 | RA-12 | Not run
EXEC-093 | W14-01 | Not run
EXEC-094 | W14-02 | Not run
EXEC-095 | W14-03 | Not run
EXEC-096 | W14-04 | Not run
EXEC-097 | W14-05 | Not run
EXEC-098 | W14-06 | Not run
EXEC-099 | W14-07 | Not run
EXEC-100 | W14-08 | Not run
EXEC-101 | W14-09 | Not run
EXEC-102 | W14-10 | Not run
EXEC-103 | W14-11 | Not run
EXEC-104 | W14-12 | Not run

## Evidence_Index
Actual evidence inventory and protection
Blank template rows contain no supplied evidence or fake digest. Store protected artifacts outside this workbook and record authoritative references.
Evidence ID | Execution / change / requirement | Actual artifact reference | Digest / integrity method | Target / scope / revision | Observed UTC / collector | Classification / access / retention | Reviewer / freshness disposition
EVD-001
EVD-002
EVD-003
EVD-004
EVD-005
EVD-006
EVD-007
EVD-008
EVD-009
EVD-010
EVD-011
EVD-012
EVD-013
EVD-014
EVD-015
EVD-016
EVD-017
EVD-018
EVD-019
EVD-020

## Defects
Observed defects and deviations
Unpopulated actual finding register. Reference threat prompts in the architecture kit are not live vulnerabilities.
Defect ID | Observed fact / scope | Expected design / requirement | Impact / priority rationale | Actual owner | Status | Recovery / correction | Retest evidence | Disposition authority / deadline
DEF-001 |  |  |  |  | Not raised
DEF-002 |  |  |  |  | Not raised
DEF-003 |  |  |  |  | Not raised
DEF-004 |  |  |  |  | Not raised
DEF-005 |  |  |  |  | Not raised
DEF-006 |  |  |  |  | Not raised
DEF-007 |  |  |  |  | Not raised
DEF-008 |  |  |  |  | Not raised
DEF-009 |  |  |  |  | Not raised
DEF-010 |  |  |  |  | Not raised
DEF-011 |  |  |  |  | Not raised
DEF-012 |  |  |  |  | Not raised

## Gate_Decisions
Gate and operating authority decisions
NO AUTOMATIC APPROVAL • G4 initial readiness is a production G3 prerequisite; continuing G4 afterwards is not a substitute. Restricted fixture permission is separate.
Gate ID | Purpose | Owner role | Required prior scope | Evidence / required records | Actual decision | Issuer / record | Validity / conditions | Actual evidence
G0 | Design adoption | Architecture authority | None | AK-01–AK-08; adopted controls and variation decisions | Not issued
G1 | Foundation acceptance | Foundation/service owner | G0 for affected scope | EK-01/02; IK-02/03; trusted access and transport evidence | Not issued
Restricted fixture | Non-production test permission | Test/change authority | G1; installed safeguarded candidate resources | Test scope, disposable data, restoration plan, exact target and expiry | Not issued
G2 | Platform and shared-service qualification | Platform/service qualification authority | G0/G1; authorized fixture; applicable observed tests | EK-03–EK-09; IK-04–IK-06; actual supported tuple and measured envelope | Not issued
G4 initial | Operational/recovery readiness | Operations + data/service acceptance | Relevant qualified platform/service | IK-07; current owners, incident path, monitoring, keys/catalogue and required restore proof | Not issued
G3 | Production activation | Authorized service acceptance owner | G0, G1, G2, applicable G4 initial; valid authority | Current tenant build evidence, exposure scope, rollback/containment and acceptance | Not issued
G4 continuing | Continuing operations and reacceptance | Operations/service owner | Activated service; approved cadence and change triggers | Maintenance, drift, recovery exercises, incidents, support and retirement records | Not issued

## Handover
Operational handover and initial readiness
Complete applicable initial readiness before production; post-activation handover confirms an already accepted scope.
ID | Readiness area | Required record | Actual owner | Status | Evidence | Decision / condition
H01 | Named service/operations/data/security owners | Actual contacts, escalation and on-call coverage |  | Not started
H02 | Accepted as-built and native ownership | Topology, versions, resource identities and tool/writer responsibilities |  | Not started
H03 | Accepted service and failure envelope | Actual limits, SLO, RTO/RPO, maintenance and capacity basis |  | Not started
H04 | Monitoring and evidence protection | Event/health coverage, loss behaviour, access and retention |  | Not started
H05 | Incident and containment authority | Scoped response, emergency paths and explicit release |  | Not started
H06 | Credential, certificate and key custody | Protected references, role separation, revocation and tested recovery |  | Not started
H07 | Backup/catalogue and initial restore proof | Accepted consistency, retained copies, key access and measured recovery |  | Not started
H08 | Support and lifecycle readiness | Compatible patch/change method, support expiry and supplier access |  | Not started
H09 | Retained data and disposal responsibilities | Holds, copy lineage, owners, key lifetime and sanitization |  | Not started
H10 | Actual initial G4 decision | Scope-specific reviewed evidence and attributable authority before G3 |  | Not started

## Recovery_Record
Actual recovery, migration and failback results
Service scope and consistency matter. All initial result fields remain Not run; no RTO/RPO or product support is pre-certified.
Exercise ID | Failure / source / target | Scope / RTO / RPO definition | Writer / fencing evidence | Keys / catalogue / dependencies | Actual recovered point / time | Data / security acceptance | Result | Authority / evidence
REC-01 | [6 empty] | Not run
REC-02 | [6 empty] | Not run
REC-03 | [6 empty] | Not run
REC-04 | [6 empty] | Not run
REC-05 | [6 empty] | Not run
REC-06 | [6 empty] | Not run
REC-07 | [6 empty] | Not run
REC-08 | [6 empty] | Not run

## Retained_Copies
Retained copies, holds, keys and disposition
Live-service retirement is separate from disposal of all data. Populate actual copies and obligations; identifiers below are empty record slots.
Record ID | Former WSD / copy identity | Location / access scope | Retention / hold / owner | Required key / catalogue | Approved live cleanup | Sanitization method / evidence | Remaining obligation / next review
COPY-01
COPY-02
COPY-03
COPY-04
COPY-05
COPY-06
COPY-07
COPY-08
COPY-09
COPY-10

## Change_Log
Controlled change and approval-impact register
A material change can invalidate previous qualification or evidence. Record the affected scope and actual authority rather than rewriting history.
Change ID | Date / owner | Scope / baseline revision | Affected architecture / interfaces | Build / rollback / safe stop | Required re-verification | Approval / execution evidence | Status
CHG-01 | [6 empty] | Not started
CHG-02 | [6 empty] | Not started
CHG-03 | [6 empty] | Not started
CHG-04 | [6 empty] | Not started
CHG-05 | [6 empty] | Not started
CHG-06 | [6 empty] | Not started
CHG-07 | [6 empty] | Not started
CHG-08 | [6 empty] | Not started
CHG-09 | [6 empty] | Not started
CHG-10 | [6 empty] | Not started

## Start
IMPLEMENTATION KIT ¦ EXECUTION AND ACCEPTANCE
Assign actual scope, owners and evidence before execution. All reference procedures start not run; no gate decision is supplied. Counts are record-quality indicators, never authorization.
Implementation deliverables |  | 10
Reference steps not run |  | 61
Unresolved applicability |  | 104
Test result rows not run |  | 104
Gate decisions not issued |  | 7
1 • Preflight | Use RB-00 and IT §1. Identify the authorized target and controlled engineering release.
2 • Commission | Select P0–P6 work and one vendor track; preserve native ownership and dependency handoffs.
3 • Qualify | Restricted disposable fixtures generate observations; they cannot authorize production.
4 • Ready / activate | G0/G1/G2 and applicable initial G4 plus current tests and valid operating authority precede production G3.
5 • Evidence | Use distinct execution IDs for each actual run and record actual scope, result, reviewer and protected artifact.
6 • Operate | Handover current as-built, recovery, support, incidents, capacity and retained obligations; re-evaluate material changes.